## Deliverable list
SÖDERENERGI AB
BIOCCS IKV
Document name: |  | FEED Document delivery list - This is in general terms what the Purchaser foresees as the main contents of the FEED and the document delivery time schedule
Date / Rev. / Sign: | 2024-02-16
Discipline | Document | Maturity Level | Description Level of Information in docuemnt | For information (Provided by SÖE) | Deliverable (By FEED Supplier) | Column2 | Delivery 1 - Concept selection and PFD review, Design Freeze | Delivery 2 - For P&ID review | Delivery 3 - For HAZOP | Delivery 4 - For Desin review and Constructability review | Delivery 5 - Project execution and cost estimate plan | Delivery 6 - Final delivery
PD | Basis of design | Issued for FEED | Input to FEED - Plant and equipment codes, document codes. Design basis, Engineering standards, SI-units, Capacity & Availability, utilities. | x
PD | Basis of design | issued for detail design | Updated with findings from FEED. Input to EPC-phase. Plant and equipment codes, document codes. Design basis, Engineering standards, SI-units, Capacity & Availability, utilities. |  | x |  | x |  |  |  |  | x
| Samrådsunderlag |  | Consultation documentation with county administraion/government. Only in Swedish | x
PD | Carbon capture process configuration selection PM | Issued for concept selection | PM including information to be used as a basis for selection of an optimum Carbon capture configuration. Including overview PFD, overview heat and mass balance data and evaluation matrix. |  | x |  | x |  |  |  |  | x
PD | Concept selection PM | Issued for concept selection | PM describing the selected process configuration for the whole project scope from capturing to ship export. The PM should also include reference to main assumptions and decisions made during the concept selection phase. Including overview PFD, overview heat and mass balance data for the whole project scope. |  | x |  | x |  |  |  |  | x
PD | Basic design report/FEED report | Issued for detail design | Goal and Purpose with the plant Stakeholder requirements Technical requirements Main functions Solutions options Safety principles Site and footprint analysis Environmental program Risk Analysis Project description and Execution plan for the next phase Cost Calculation Updated basis of design including ambient conditions |  | x | [6 empty] | x
PD | Process description | Issued for detail design | Describe the functionality of the main sections of the plant including main control loops, main operation cases (import/export, carbon capture active/not active), load variation, start/stop and idling/standby. The document shall also describe the interaction between the sections and how load variations and different operation conditions are handled in principle. |  | x |  | Draft | x | x |  |  | x
PD | Operation philosophy | issued for detail design | Description of operation philosophy including estimation of number of staff, control rooms, remote control/operation if applicable. To be used as a basis for OPEX-calculations. |  | x | [6 empty] | x
PD | Mass & Energy Balance - Stream data table | Issued for detail design | Including but not limited to: Material flows for incoming, outgoing and relevant internal streams including emission and effluent streams. Operating range including for example temperature, pressure, composition, moiture content, etc. Design data including for example temperature, pressure, composition, etc. Heat and cooling demand from external sources (electricity, municipal heating water and cooling water) and major internal equipment. Major utility systems such as cooling system shall be included. Heat and mass balance data within a package delivery may be simplified if guaranteed by a vendor. The results shall be presented in a stream data table refering to streams and equipment at the PFD. |  | x |  | x |  | x |  |  | x
PD | Process Calculation | Issued for detail design | Calculation report describing input, method and results for relevant calculation. Including but not limited to: Methodology for heat and mass balance calculations. Dimensioning calculations for the transport pipeline from the carbon capture section to the liquefaction section. |  | x | [6 empty] | x
PD | Process Flow Diagram PFD - Main process | issued for detail design | As a minimum showing: main equipment, main streams, incoming and outgoing streams, duty for heat exchangers and motors. A stream data table showing results from the heat and mass balance shall be referring to the PFD. Naming acording to SÖE standrad. |  | x |  | x |  |  |  |  | x
PD | Process Flow Diagram PFD - Utilities | issued for detail design | As a minimum showing: main equipment, main streams, incoming and outgoing streams, duty for heat exchangers and motors. A stream data table showing results from the heat and mass balance shall be referring to the PFD. Naming acording to SÖE standrad. |  | x |  | x |  |  |  |  | x
PD | Piping & Instrument Diagram P&ID - Main process and utilities | Issued for P&ID review Issued for HAZOP Issued for detail design | Including incoming/outgoing streams, interconnecting streams with reference to related PID:s, main equipment, pipelines (including dimension, pipe class, media, heat tracing and insulation), instrument (including control valves), automated valves, manual valves, relief valves, main control loops. Utility supply/connections may be shown with general location. Location of drain and vent valves may be indicated with general location. Naming acording to SÖE standrad. As a proposal minimum one P&ID is prepared per section and one per main utility systems (such as cooling water system). P&ID for package deliveries may be simplified if functionality is guaranteed by a vendor. Updated after P&ID-review. Main findings implemented. Updated after HAZOP. Main findings implemented where applicble. |  | x |  |  | x
Measurement pint list
PD | Line list Basic | issued for detail design | Critical process lines and major piping determining equipment positions, control valves, relief valves, supports, etc. Flow, Material, Dimension, Design/operation Pre/temp, min/norm/max, Media, media class, Line-nr, Area-nr, to/from, PED/AFS. Naming acording to SÖE standrad. |  | x | [6 empty] | x
PD | Equipment list Basic | issued for detail design | Design/operation press/temp, Media, main dimensions. Naming acording to SÖE standrad. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x | [6 empty] | x
PD | Valve list Basic | issued for detail design | Manual valves in main process, type, design/operation press/temp, media. Naming acording to SÖE standrad. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x | [6 empty] | x
PD | Utility consumption list | issued for detail design | Information to Client |  | x |  | x |  |  |  |  | x
PD | Safety/Relief valve philosophy | issued for detail design | Main philosophy for pressure relief. |  | x | [6 empty] | x
PD | Safety/Relief devices list | issued for detail design | List of main relief devices. Type (proposed), design/operation press/temp, media, dimensioning flowrate. |  | x | [6 empty] | x
PD | Battery Limit List | issued for detail design | Including flow specification and reference to the PFD data table. |  | x |  | x |  |  |  |  | x
PD | Emissions and Effluents List | issued for detail design | Including flow specification and reference to the PFD data table. |  | x |  | x |  |  |  |  | x
PP | 3d Model | issued for detail design | For visualization including but not limited to main equipment, main piping and ducts, main pipe racks, main steel structures including stairs and floors/levels and fence. NWD files viewable in Navis |  | x |  |  |  |  | x |  | x
PP | General Layout / Plot plan | issued for detail design | Layout for larger equipment, piping and ducts to show how all componenets fit within the process area. Main escape routs to be indicated and building structures. |  | x |  | x | x | x | x | x | x
PP | Piping Material Specification | issued for detail design | Description of material selection based on media, pressure, temperature, pH and other relevant factors.. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x | [6 empty] | x
PP | Insulation General Specification | issued for detail design | Generall demand acroting to SSG7591 but need to include overview of cold service for liquid CO₂, winterisation, heat tracing and other deviations to insulation. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x | [6 empty] | x
PP | Material Take off - Piping | issued for detail design | Main Piping, pipe fittings and pipe supports. To be used for cost estimation purposes. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x | [6 empty] | x
PP | Valve Specification | issued for detail design | Type, design/operating press/temp, material. For cost estimate purposes. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x | [6 empty] | x
MD | Equipment data sheets | issued for detail design | For main equipment and packages including information for request for quotation and/or dialogue with vendors. | [8 empty] | x
MD | Technical specifications (Mechanical) | issued for detail design | For main equipment and packages including information for request for quotation and/or dialogue with vendors. |  | x | [6 empty] | x
MD | Equipment drawings | issued for detail design | General arangment drawings for main components and packages as input to layout preparation, for consturctability and transport review. |  | x | [6 empty] | x
K | Main structural layouts, elevations, sections | issued for detail design | General arrangement drawings with necessary sections. For package deliveries this information may be supplied by the vendor. Main escape routs to be indicated. |  | x |  | x | x | x | x | x | x
K | Building and work description | issued for detail design | Description of buildings (type, function, snow load, HVAC, electrification, lighting etc) |  | x |  |  |  | x |  |  | x
K | Civil and structural design | issued for detail design | Description of Civil and structural design |  | x |  |  |  | x |  |  | x
K | Loads affecting foundations and grade | issued for detail design | All loads necessary for designing foundations and ground works. |  | x |  | x | x | x | x | x | x
K | Ground preparations due to Construction/Erection | issued for detail design | All information that is needed for preparations performed by SÖE |  | x |  |  |  | x |  |  | x
K | Drainage philosofy | issued for detail design | Description of pits, oil sumps, sewage water, storm water and so on. |  | x |  |  |  | x |  |  | x
K | Material Take off - Foundations, structural steel and buildings | issued for detail design | Main Foundations, structural steel constructions, main piperacks and buildings. To be used for cost estimation purposes. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x |  |  |  | x |  |  | x
M | Civil Engineering summary report | issued for detail design | Civil overview report (CC, transportation and Liquefaction, and storage) |  | x |  |  |  | x |  |  | x
M | Construction areas and laydown areas | issued for detail design | Overall construction plan. Deffinition of laydown areas for large equipment |  | x |  |  |  | x |  |  | x
M | Hydraulic Design Report of drainage system | issued for detail design | Description of drainage system including proposed elevations. No detailed hydraulic calculations required. |  | x |  |  |  | x |  |  | x
M | Underground CO₂ piping description | issued for detail design | Description of proposed method for construction for the underground CO₂ transport pipeline. Including type of construction for different stretches of the pipeline, description of installation method (high level), describing sectional drawings/sketches (high level). |  | x |  |  |  | x |  |  | x
M | Underground CO₂ piping overview drawing | issued for detail design | Shwowing the proposed method of installation for the different stretches of pipeline, crossing of roads and other main infrastructure. |  | x |  |  |  | x |  |  | x
M | Material Take off - Ground | issued for detail design | Main earthworks for the process sites and along the underground CO₂-pipeline. To be used for cost estimation purposes. Data within package deliveries may be simplified if functionality is guaranteed by a vendor. |  | x |  |  |  | x |  |  | x
E | Technical Specifications Electrical Equipment | issued for detail design | For main equipment such as switchgear, transformers, VSD's. Preliminary specifications including information for request for quotation and/or dialogue with vendors. |  | x | [6 empty] | x
E | Motor List (Consumption List) | issued for detail design | Main equipment motorlist. Including installed power, estimation of operation demand and different operation modes. Proposal for critical equipment for dimensioning of emergency power sulpply and UPS. |  | x | [6 empty] | x
E | Cable Routing (Main Racks) | issued for detail design | Routing to the larger consumers (for example the compressor) |  | x | [6 empty] | x
E | Electrical Rooms / Buildings - Layout (Space Reservation) | issued for detail design | Estimation of size and preferably a 2D drawing showing main equipment and cabinets. |  | x | [6 empty] | x
E | Single Line Diagram | issued for detail design | Power Distribution to main consumers. |  | x |  |  |  |  | x |  | x
E | Overview of Fire Detection Systems | issued for detail design | General descricption, system overview. |  | x |  |  |  |  | x |  | x
E | General Electrical Design Specification | issued for detail design | General description outline main components such as transformers, MCC, (large consumers). |  | x | [6 empty] | x
E | Earthing diagram | issued for detail design | Principle Earthing principle and protection and highlighting of specilla demands if applicable | [8 empty] | x
IA | Instrument List | issued for detail design | List of main insturments. For Type, operation and design data. Data within package deliveries may be excluded if functionality is guaranteed by a vendor. To be used for cost estimation purposes. |  | x | [6 empty] | x
IA | Control Rooms / Buildings - Layout | issued for detail design | Number of operation stations. Desicription of CCTV system in text. |  | x |  |  |  |  | x |  | x
IA | Control System Description (incl. Block Diagram) | issued for detail design | System description with control system diagram, network and bus type. |  | x | [6 empty] | x
IA | Control Philosophy | issued for detail design | Control philosophy including description of main control loops and main safety interlocks. An overview desc. of the control system. |  | x | [6 empty] | x
IA | Instrument specification | issued for detail design | Where required for specific instruments or instrumented systems. Such as CO₂ analyzers, CO₂ metering and plant in/out monitoring and accountingsystem. To be used for dialogue with vendors and cost estimation purposes. |  | x | [6 empty] | x
N | Work Environmental Plan | issued for detail design | Document developed for the specific operation with main findings. To be finalized in detail design. |  | x |  |  |  |  | x |  | x
N | Fire and life safety philosophy | issued for detail design | Including but not limited to description of fire fighting systems (where applicable), handling of CO₂ leakage including directing flow of liquid and gas CO2 during a leak, measures to protect staff and surrounding areas, escape routs etc. |  | x |  |  |  |  | x |  | x
N | HSE General Specifications | issued for detail design | Description of main aspects related to health, safety and environment. Including but not limited to emissions to air and water, expected light and sound emissions. |  | x |  |  |  |  | x |  | x
N | Materials safety data sheets | issued for detail design | For chemicals expected to be used within the plant. |  | x | [6 empty] | x
N | HAZID Report and protocol | issued for detail design | HAZID summary report with main findings including protocol from the HAZID meeting. SÖE to take part in HAZID.
PD | HAZOP Report and protocol | issued for detail design | HAZOP summary report with main findings including protocol from the HAZOP meeting. SÖE to take part in HAZOP. |  | x |  |  |  |  | x |  | x
CE | Cost estimate plan | issued for detail design | Description of the methodology for cost estimation. Including but not limited to plan for dielogue with vendors and request for quotations. Shall meet the AACE internationa level 3 (or equivalent), +30/-20%. To be supplied early in the project and updated for final delivery. |  | x | [5 empty] | x | x
CE | Cost estimate calculaitons | issued for detail design | Acrodng to AACE internationa level 3 (or equivalent), +30/-20%. Calculations shall be documented and shown to SÖE upon request. |  | x - Upon request | [6 empty] | x
CE | Cost estimate reports | issued for detail design | Results from the cost estimate calculations reported on the proposed report structure (or similar, changes may be discussed during the FEED) provided in document Requirement specification. |  | x | [6 empty] | x
CE | Vendor quote documents | issued for detail design | Documents provided from vendors including quotes, technical information and general arrangement drawings shall be shared with SÖE. If NDA is required this shall be discussed with SÖE. |  | x | [6 empty] | x
All | Review reports - Self Check | issued for detail design | Self check - Shall be stored and ready for review by SÖE upon request. |  | x | [6 empty] | x
EM | Design review report | issued for detail design | Perform a design review where aspects related to layout, accessability and operation at the different sites are considered. SÖE shall participate in the review sessions. Report including a review protocol and main findings. |  | x | [6 empty] | x
EM | Constructability plan | issued for detail design | A plan for the construction phase of the project describing aspects related to constructability such as transport to site, heavy lifting, lay-down areas, construction areas, pre-fabrication at the different sites are considered. |  | x | [6 empty] | x
EM | Constructability review report | issued for detail design | Perform a constructability review where aspects related to constructability such as transport to site, heavy lifting, lay-down areas, construction areas, pre-fabrication at the different sites are considered. SÖE shall participate in the review sessions. Report including a review protocol and main findings. |  | x |  |  |  | x |  |  | x
PM | Project Description and execution plan - FEED | issued for detail design | For the FEED phase. |  | x |  | x
PM | Project Description and execution plan - CCS project | issued for detail design | For the full project up untill construction and commissioning. |  | x | [5 empty] | x | x
PM | Project Organization - FEED | issued for detail design | For the FEED phase. |  | x |  | x
PM | Project Organization - Next phase | issued for detail design | Proposal of organisation for the next phase |  | x | [5 empty] | x | x
PM | Project Time schedule - FEED | issued for detail design | Timeplan including activities, milestones, reviews and risk analysis. For the FEED phase. |  | x |  | x
PM | Project Time schedule - CCS project | issued for detail design | Timeplan including main/overall activities, milestones, reviews and risk analysis. For full project including construction phase and commissioning. |  | x | [5 empty] | x | x
PM | Procuremnet plan | issued for detail design | Procurement plan to establish when long lead equipment, equipment and construction needs to be purchased. |  | x | [5 empty] | x | x
Abbrevations | Description
PD | Process engineering
PP | Piping engineering
E | Electrical Engineering
M | Civil Engineering
N | Risk and Safety
CE | Cost engineering
EM | Engineeering manager
PM | Project Manageer
A | Architcture
K | Building construction & engineering
IA | Instrumentation & Automation engineering
MD | Mechncial Engineering